## Sheet1
Risk | Probability | Impact | Planning Strategy | Action
Suppliers Delay | Medium | Medium | Avoid | Get from another supplier to avoid delay
Security | Medium | High | Avoid | Hire cyper security team.
Servers Down | Low | High | Accept
Delay in development | Medium | Medium | Avoid | Follow the time plan according to the project.
Delay in testing | Low | Medium | Avoid | Prepare tesing according to requirements before Development.