## Sheet 1
Duration | PV | AC | EV
0 | 0 | 0 | 0
7.5 | 5000 | 7000 | 5500 | Yes, the project is over budget by 1500 hrs.
15 | 10000 |  |  | No, it is ahead by 500 hrs, which is equivalent to 10 days (5 Engineers, 9 Working Hrs/Day)