## Tools and Services
Task | Count | Price per one $ | Cost in $
Security | 70 |  | 15000
Liscenced Programs | 30 | 50 | 1500
Liscenced Windows | 10 | 100 | 1000
Strong Antivirus | 10 | 150 | 1500
Buy Suppliers | 10 | 1000 | 10000
Test Suppliers | 10 | 100 | 1000

## Working Hours
Task | HRS | Cost | Cost/hr $
Training | 140 | 2200
Courses | 80 | 1600 | 20
Workshops | 60 | 600 | 10
Security | 68 | 1610
Install Flutter SDK | 3 | 60 | 20
Install Proper IDES | 5 | 100 | 20
Design Code | 10 | 300 | 30
Test Code | 40 | 800 | 20
Review Code | 5 | 200 | 40
Integration Testing | 5 | 150 | 30

## Assumptions
The client must pay for the Firebase after 3 years
The client is responsible for paying for extra storage space on the server
The company is responsible for publishing the APP on google play and IOS store
The client is responsible for hiring a customer service company
The company is responsible for training the customer service company